4 th QUARTERLY REPORT

Improvement of the safety, quality and availability of organs, tissues and cells for transplantation Member State Partner The Ministry of Health of Italy In cooperation with National Transplant Centre Beneficiary Country Partner Ministry of Health of the Slovak Republic BC Final Recipient University Hospital Ružinov in Bratislava (Slovak Republic) 04 December 2007

Table of Contents

ABBREVIATIONS	3

Section 1. Project data	4

Section 2. Content 	5

2A – Background	5

Project assumptions	6

Achievements of mandatory results	7

Activities in the reported period 	8

Activities of Component II : 	10

Design and implementation of unified management system	10

- 2.2.1 , 2.2.2 , 2.2.3  Short Term Courses and Medium Term Courses:	10

4.1, 4.2    Preparation of guidelines, brochure, leaflets  and dissemination materials	14

Timing & Delays 	16

Adherence to schedule	16

Recuperation of delays	16

ASSESSMENT	16

Overall assessment of progress	16

Issues arisen	18

Recommendations	22

Name of services / goods purchased or direct costs	23

ANNEX 1	26

ANNEX 2	32

ANNEX 3	40

The European policy	42

in the field of organs, tissues and cells donation and transplantation	42

Slovak legislation	43

The twinning program between Italy and Slovak Republic	43

Critical aspects in the donor management and transplant process	44

The QMS guidelines	44

# ABBREVIATIONS

| BC | Beneficiary Country (Slovakia) |
| --- | --- |
| CA | Contracting Authority |
| CFCU | Central Financing and Contracting Unit |
| CNT | Centro Nazionale Trapianti (Italian National Transplant Centre) |
| CTB | Central Tissue Bank |
| DPL | Deputy Project Leader |
| DPM | Deputy Project Manager |
| FRP | Final recipient of the Action (University Hospital Bratislava) |
| HCB | Hemopoietic Cell Bank |
| IEB | International Eye Bank |
| IT | Italian Republic |
| MoH | Ministry of Health |
| MS | Member State (Italy) |
| MSP | Member state partner (CNT) |
| PL | Project Leader |
| PLs | Project leaders |
| PM | Project Manager |
| RTA | Resident Twinning Advisor |
| RTA-A | Resident Twining Advisor - Assistant |
| SC | Steering Committee |
| SCOT | Slovak Center for Organ Transplantation |
| SG | Subgroup |
| SR | Slovak Republic |
| STE | Short Term Expert |
| TA | Technical Assistance |
| TS | Technical Specifications |
| UHB | University Hospital Bratislava |

# Section 1. Project data

| Twinning Contract No. | 200501746404-0201-0001 |
| --- | --- |
| Project title | Improvement of the safety, quality and availability of organs, tissues and cells for transplantation |
| Twinning partners | Ministry of Health (IT), in cooperation with the National Transplant Centre (IT) Ministry of Health (SK), University Hospital Ružinov in Bratislava (SK) |
| Report | 4 th Quarterly Report |
| Period covered by the report | 05 September 2007 – 04 December 2007 |
| Duration of the project | 24 months |
| Rapporteur Member State Mr. Alessandro Nanni Costa, project leader | Rapporteur Beneficiary Country Mr. Richard Rasi, project leader |

# Section 2. Content

## 2A – Background

Policy Developments

1. 1. Beneficiary Country policy developments in the sector

The Ministry of Health of Slovak Republic (MoH SR), as a central state administration body in the health sector, is responsible for implementation of Directive 23/2004/EC in general and it has appointed, by its decision, tissue establishments to be responsible for direct implementation and execution of that Directive in the praxis.

In the area of tissue, cells and organ procurement and transplantation there are two main types of organizations: 1) tissue establishments and 2) organ transplantation centres.

1. 2. Beneficiary institutions and other parties involved

The first tissue establishment in the Slovak Republic was linked to Ružinov General Hospital in Bratislava and started its activity in 1988. The list of currently existing tissue establishments under the competence of the SR Ministry of Health is as follows:

- Central Tissue Bank, University Hospital Ružinov, Bratislava, multi-tissue bank

- Associated Tissue Bank, University Hospital and Medical School, Košice, multi-tissue bank

- International Eye Bank, Petržalka University Hospital, Bratislava , eye bank

- International Eye Bank, F.D.Roosewelt Hospital, Banská Bystrica, eye bank

- Hemopoietic Cell Banks  (HPC banks)  -  3 in Bratislava, 1 in Banská Bystrica, 1 in Martin, 1 in Košice, 1 in Prešov

In addition, there are non-governmental and private organisations such as:

- Slovak Register of Cord Haemopoetic Cells (EUROCORD), Bratislava, cord blood bank

- Private Hospital Košice - Šaca Tissue Bank

As regards organ transplantation centers, all of them are under the responsibility of the MoH as follows:

- Slovak Centre for Organ Transplantation – Slovak Medical University (SCOT) with 5 Regional Transplantation centres

  - Transplant centre University Derer’s hospital, Bratislava (kidneys, liver)

  - Transplant centre, Slovak institute for heart diseases, Bratislava, (heart)

  - Transplant centre University hospital, Martin (kidneys)

  - Transplant centre Roosevelt hospital, Banská Bystrica (kidneys, pancreas)

  - Transplant centre, University hospital, Košice, (kidneys)

The public awareness towards organ, tissues and cells donation is very low in Slovakia. The main reason for this is a lack of financial resources. The result is a very low rate of donations, which achieves annually less then 10.2 donations in 2004 per 1 million of inhabitants in organ transplantation.

A reason why problems such as a lack of donors and long waiting lists for organ donations occur is the presently unsatisfactory information system that is not unified, and interconnected, neither between the tissue establishments, nor with the Central donor and non-donors register located at the SCOT in Bratislava. This means that for example information about a possible donor in one tissue establishment is not at disposal in the whole network. Secondly, the information system for organ transplantation does not include the requirements of tissue and cell establishments and it is not compatible with the requirements of the Directive 23/2004 EC. A central information system managing waiting and donor lists for organ donations is already 10 years old and needs to be upgraded. The required data confidentiality, data protection, and data storage time cannot be as yet fully assured.

Additionally, each tissue establishment elaborated its own quality management system, which mostly does not conform to contemporary regulatory and quality requirements of the European Communities. These systems strongly need to be unified as well as updated according to the latest EC Directive 23/2004/EC.

Regarding the institutional framework of the quality control, it is monitored by national authorities: Slovak National Accreditation System (SNAS) and State Institute for Drug Control (SIDC). SNAS controls the good laboratory praxis, and SIDC is responsible for good manufacturing praxis.

Establishments have to fulfil the accreditation criteria as ruled by the above-mentioned authorities. The project will give a framework for compatibility of national and EC requirements for safety and quality management in field of organ, tissue and cell transplantation.

### Project assumptions

The assumptions as formulated in article 3 of the Work plan are

- Current legislation in force

- Trained staff  will stay on their positions, using the acquired knowledge

- Institutions involved in the unified info system cooperate and actively use the system

- Willingness of particular institutions to participate and provide data

- Relevant staff available for planned training

- Technical facilities available for the training

The above mentioned assumptions imply that, using the current legislation in force, in particular the ones entered into force on 2006 and at the beginning of 2007, the institutions and all involved staff will actively participate at the project taking advantage of the planned training, using their acquired knowledge, providing data and actively using the unified info system. Staff and hospital facilities will be fully available for planned training.

#### Project objectives

- General: Ensure a high standard of quality and safety for donation, processing and distribution of human tissues and cells in the Slovak Republic to achieve a satisfactory implementation of the European Community Directive 2004/23/EC.

- Specific: Introducing quality management for organ transplantation, tissue and cell banking, to assure the highest possible level of public health protection.

Benchmarks

- The facilities included in the project accredited by the beginning of 2009, fulfilling the requirement of the directive 2004/23/EC. Following some delays in the finalization of the Twinning Contract and the start up of the project on 4th December 2006 with its conclusion on November 2008, it has become necessary to postpone the date of accreditation of the facilities, which originally was foreseen by the end of 2007.

- Increasing the number of successful transplants

- Increasing the number of real donors from indicated donors by 10%.

- Decreasing the insufficient number of donors by 5%.

- 100 employees of tissue and cells establishments and organ transplant centres  trained on QMSG

- tissue and cells establishments and organ transplant centres  using new developed system by the end of the project (in the contract originally foreseen by the end of 2007)

## Achievements of mandatory results

- Audit  report produced corrective and preventive action plans in place / Component I

- QMS for tissue and cells establishment and transplantation centres developed and introduced:

Quality management system guide (QMSG) developed

Tissue establishment and transplant centre staff trained / Component II

- Unified information system for transplantation centres, tissues and cell establishments (developed and implemented within TA contract) and tested / Component III

- Proper public dissemination of the project outcomes/Guidance brochure / Component IV

The following MANDATORY RESULTS were completed during the period of time herein reported:

Component 2:

- Provision of  Medium and Short Term Courses for trainees coming from organ, tissue and cell establishments in Slovakia

Component 4:

- Development of  Brochure for donation and transplantation centres in Slovakia as synthetic version of Quality Management System Guide for organs, tissues and cells

- Development of Leaflet for public to support awairness campaign by MoH regarding donation and transplantation in Slovakia

- Preparation of November 2008 Closing Conference and related press conference

## Activities in the reported period

Here below is a table summarising the STE missions.

| Activities | Name of expert | Dates of mission | Topic | Total days in the workplan | Days worked | Completed % |
| --- | --- | --- | --- | --- | --- | --- |
| Project Coordination |  |  |  | 8 | 1 | 12,50% |
|  | GANASSI AGGER Simona | 19-20 September 2007 |  |  | 1 |  |
| Activity 2.2 | Provision of set of specialized trainings | 106 | 44 | 41,50 % |
|  | FEHILY Deirdre | 17-21 September 2007 |  |  | 4 |  |
|  | PICCOLO Giuseppe | 17-21 September 2007 |  |  | 4 |  |
|  | MIGLIACCIO Giovanni | 17-21 September 2007 |  |  | 3,5 |  |
|  | VALERI Maurizio | 17-21 September 2007 |  |  | 4 |  |
|  | INTRONA Martino | 18-20 September 2007 |  |  | 2 |  |
|  | PORTA Eliana | 18-21 September 2007 |  |  | 3 |  |
|  | PONIATOWSKI Stefan | 17-21 September 2007 |  |  | 4 |  |
|  | FEHILY Deirdre | 24-28 September 2007 |  |  | 3 |  |
|  | PICCOLO Giuseppe | 24-28 September 2007 |  |  | 3 |  |
|  | VALERI Maurizio | 24-28 September 2007 |  |  | 3 |  |
|  | LOMBARDINI Letizia | 24-27 September 2007 |  |  | 2,5 |  |
|  | PIANIGIANI Elisa | 24-29 September 2007 |  |  | 3 |  |
|  | RIDOLFI Lorenza | 14-16 October 2007 |  |  | 2 |  |
|  | PETTINAO Paolo | 15-16 October 2007 |  |  | 1 |  |
|  | ZANELLO Marco | 15-16 October 2007 |  |  | 1 |  |
|  | GIORDANO Francesco | 15-16 October 2007 |  |  | 1 |  |
| Activity 4.1 | Preparation and development of the guidelines brochure | 15 | 6 | 40,00 % |
|  | BARIANI Fiorenza | 12-15 November 2007 |  |  | 2 |  |
|  | DI CIACCIO Paola | 12-15 November 2007 |  |  | 2 |  |  |
|  | GENTILE Margherita | 12-15 November 2007 |  |  | 2 |  |  |
| Activity 4.2 | Preparation of the leaflets and dissemination materials | 10 | 3 | 30,00 % |
|  | BARIANI Fiorenza | 12-15 November 2007 |  |  | 1 |  |
|  | DI CIACCIO Paola | 12-15 November 2007 |  |  | 1 |  |  |
|  | GENTILE Margherita | 12-15 November 2007 |  |  | 1 |  |  |

3rd STEERING COMMITTEE MEETING

The  third Steering Committee was held on September  19th 2007 at MoH in Bratislava. The participants were: RTA Mr. Lauro, RTA-A Ms Kotzigová,  PM Mr Koller, SPO Mr Skorvaga, Ms Vallova (MoH),CFCU Mr Škvarka, DPL Ms Agger. The progress of the project during last 3 months (June-July and August 2007) was discussed, together with the 3rd quarterly report.

A plan for the following activities was made and it will be reported in the next paraghraphs.

## Activities of Component II :

## Design and implementation of unified management system

All the Activities will be described in this section and commented in the Assessment  section.

- 2.2 Provision of set of specialized trainings

### - 2.2.1 , 2.2.2 , 2.2.3  Short Term Courses and Medium Term Courses:

2.2.1   Original design of  SHORT TERM COURSES:

These courses were originally foreseen  in the twinning contract with the aim to cover general aspects of organ and tissue donation and procurement such as:

-transplant procurement management,

-donor detection, identification and clinical evaluation,

-brain death diagnosis,

-non heart beating donors,

-clinical examination simulation,

-donor maintenance,

-family approach for organ and tissue donation,

-application of selection criteria,

-review of clinical cases,

-retrieval organization,

-organ procurement,

-tissue procurement, packaging and labelling,

-allocation system,

-ethics and legislation.

-  Reviewing topic of  SHORT TERM COURSES:

During a meeting in Bratislava at the end of March between the RTA Mr Lauro, the DPM Mr Kuba and the STE Mr Ghirardini it was stated by DPM that the level of expertise of transplant coordinators and anesthesiologists (responsible for donation and procurement of organs and tissues in Slovakia) is nowadays higher than expected in the original version of the twinning contract.

Two useful suggestions were made to RTA by Mr Kuba and Mr Ghirardini separately, in order to develop a Short Term Course more advanced than foreseen in the contract and consequently more useful and updated: Mr Kuba suggested the participation of the Italian PL Mr Nanni Costa with RTA at the local ETCO (European Transplant Coordinators Organization) course, held in Jahodna-Kosice at the end of April 07, in order to understand clearly the level of knowledge and expertise of  transplant coordinators and local anesthesiologists. Mr Ghirardini suggested to add - as an additional activity to the twinning contract - some Site Visits on Slovak coordination centres located in Bratislava, Martin, Banska Bystrica and Kosice, made by Italian STEs, in order to verify the activity in the centres, to assess their training-needs and to discuss directly with local coordinators how to develop a useful Short Term Course. It was added a visit to Slovak Centre for Organ Transplantation (SCOT) in Bratislava for the same purpose and the aim to better understand the network between SCOT and coordination centres located in Bratislava, Martin, Banska Bystrica and Kosice.

Both the suggestions were discussed by RTA with Italian PL Mr Nanni Costa and were fully approved by him.

Mr Nanni Costa appointed Ms Ridolfi as a new STE in order to visit all Slovak coordination centres, as well as he appointed Ms Peritore in order to visit SCOT. He either delegated Mr Lauro (RTA) to attend the local ETCO course in Kosice. Because of the change of the Slovak SPO during April 2007, the RTA had the possibility to discuss these topics with the new SPO Mr Skorvaga only on May 2007, but he kept informed Ms Krbatova (MoH) about all these new activities.  The Slovak PL approved all these site visits to coordination centres and SCOT as well as  the new Italian STEs Ms Ridolfi and Ms Peritore.

- Re-designing  SHORT TERM COURSES:

Following all these activities, a decision was made by RTA and Italian STEs in order to         change the topic of Short Term Courses. RTA discussed it at the May monthly meeting with new SPO, Mr Skorvaga and CFCU Mr Skvarka. Italian CNT fully approved the change.

The draft of the 2-days Short Term Course has  foreseen a first day dedicated to an “interactive course”, with Italian and Slovak “teachers” together performing “role playing” meetings inside small groups of trainees : they were supposed to discuss with Slovak coordinators and anesthesiologists how to better organize the network of donations and transplantations in Slovakia. Slovak coordinators and anesthesiologists were supposed to interact with Italian STE and DPM Mr Kuba (responsible for SCOT-Bratislava) in order to actively discuss the way of improving the network between coordination centres and designing a common “organizative model “of a coordination centre. A second day was more conventionally dedicated by STEs to some mentions on topics like the use of marginal donors and the tissue procurement. Because of the re-designing of the course and the fact that there was a local ETCO course held recently in Slovakia, the plan was to postpone this course after the deadline of August 31st 2007, into the autumn time (October 2007).

- Development of  SHORT TERM COURSES:

The Short Term Course was held on October 15th and 16th , 2007 at Ruzinov hospital in Bratislava.

The programme, list of participants and Ms Ridolfi's comments (agreed with Mr Kuba)  related to this course are enclosed in this report as Annex 1, while slide presentations are enclosed as a CD.

The course was coordinated by Italian STE Ms Ridolfi.

MoH sent an official  letter of invitation to the head-coordinators  of 4 coordination centres in Slovakia.

RTA and RTA-A sent an official invitation by email as well, while later the twinning team contacted personally by emails and phone calls all the potential participants (the list of contacted persons  is included in Annex 1).

The course was attended by 14 participants (coordinators and anesthesiologists) coming from different areas of Slovakia.

During the course, the lectures were given by 4 Italian STEs (Ms Ridolfi, Mr Zanello, Mr Pettinao and Mr Giordano), by Mr Kuba  (as responsible of SCOT-Bratislava) and by 3 Slovak coordinators coming from Bratislava (Mr Krsek) , Martin (Mr Miklusica)  and Kosice (Mr Hudak) area. Mr Nanni Costa could not attend the course and he was replaced by Ms Ridolfi. Also Mr Sykora (coordinator from Banska Bystrica area) was not able to attend the meeting, but Banska Bystrica Coordination Centre sent two trainees anyhow.

The first day was dedicated to compare the two different regional and national coordination systems between Slovakia and Italy - followed by a round table on this topic, while the second  day was dedicated to an active discussion on donation process and related clinical cases. Moreover the results so far achieved through the TW project  were reported by RTA.

Simultaneous translation was available and the slides were projected in Slovak language.

MoH supported financially the CME credits (SACCME credits) for the participants and the refreshments.

In the Assessment section, there will be added some technical comments to this course.

2.2.2 , 2.2.3 MEDIUM TERM COURSES:

Generally MEDIUM TERM COURSES were dedicated as per TW contract to transplant centre trainees in order to teach them how to apply and use on a daily working basis the QMSGuide, developed in the previous phase of the project by Italian and Slovak STEs in order to foster in Slovakia the EU Directives regarding transplantation.

2.2.2  Designing  MEDIUM TERM COURSES addressed to tissue establishments:

Such courses were delivered as contribution of STEs to the already designed 1-year training for tissue bank personnel that was performed in SR. Particular contents were agreed by IT and SK in-the-field experts upon discussion of the syllabus of this course in the period of QMSG development. The main change, decided by Slovak and Italian experts during the development of QMSGuide, was to add the HPC bank trainees to the course, as the QMSGuide is dedicated to cell transplantation as well. This suggestion was made by Italian and Slovak experts, together with coordinator of tissue medium term courses Ms Fehily, DPM Mr Kuba and PM Mr Koller and it was presented and fully discussed at the May monthly meeting by RTA with the SPO Mr Skorvaga and CFCU Mr Skvarka.

2.2.3   Designing  MEDIUM TERM COURSES addressed to organ transplantation centers:

The course will focus on the application of quality management principles derived from the quality system management guide as far as organ transplantation centers are concerned.

In this case the experts will make some suggestions, because there still are no precise EU directives on QMSGuide for organs.

- Development of  MEDIUM TERM COURSES

These specific trainings provided an explanation of the specific parts of the QMSGuide according to each group’s specialization. Trainings were foreseen inside the contract  for about 50 health care personnel and 50 staff of tissue and cells establishments and organ transplantation centers. They were foreseen as 8 days courses at Ruzinov hospital in Bratislava.

During the monthly meeting held in May, an extra financial support for the medium term courses was asked by RTA to SPO Mr Skorvaga, as inside the TW Project a financial support for travel and accomodation expenses of the Slovak trainees was not clearly foreseen.

The MoH did NOT add an extra-financial support to these courses (as per MoH statement, reported  by Mr Skorvaga during the following July monthly meeting).

The Italian CNT-Roma (Italian National Transplant Centre) decided indeed to support these courses, affording the expenses of CME credits (SACCME credits) for participants and refreshments during the courses.

Medium term courses (MTC) were foreseen by the TW contract to be held during July and August 2007. A decision was made by Slovak and Italian experts to postpone them on September 2007 (the foreseen deadline was August 31st 2007), in order to obtain an increased attendance of Slovak trainees. This decision was communicated by RTA to MoH (Mr Skorvaga) during May monthly meeting as well.

The courses were coordinated by Italian STEs Mr Piccolo and Ms Fehily.

The courses were divided in the following way: MTC 1 (18 and 19.09.07), MTC 2 (20 and 21.09.07), MTC 3 (25 and 26.09.07) and MTC 4 (27 and 28.09.07).

The programme related to these courses is enclosed in this report as Annex 2 and the slide presentations can be found on the CD .

MoH sent 2 official letters of invitation to all Directors of transplant centres along Slovakia in order to increase the participation to these courses, while the twinning team was contacting the participants personally by email and phone calls.

The MTCs were attended by 43  participants coming from all along Slovakia.

Only 6 centers (out of 18- around 33%) did NOT participate at all at the MTcourses: 1) Liver Tx Centre in Bratislava, 2) Kidney/Pancreas Tx Centre in Banska Bystrica, 3) Kidney Tx Centre in Kosice,4) Eye Bank in Banska Bystrica, 5) HPC Bank Oncology Kramare in Bratislava, 6) HPC Bank in Kosice.

Due to the poor number of participants at the last MTC 4 (some of the trainees cancelled their presence at last moment without previous notification), this course lasted only one day: therefore the days spent over the courses were 7 instead of 8.

During the courses, the lectures were given by 8 Italian STEs (Mr Piccolo, Ms Fehily, Mr Valeri, Mr Migliaccio, Mr Introna, Ms Porta, Ms Lombardini and Ms Pianigiani), by PM Mr Koller and DPM Mr Kuba, by 2 Slovak experts (Mr Mistrik and Ms Jarabinska) and by 2 EU experts (Mr Bregeon and Mr Poniatowsky).

The programme has foreseen a first day dedicated to presentation of results of TW project by RTA, presentation of the Slovak legal framework about transplantation, QMSGuide overview about organs, tissues and cells , and discussion of clinical cases with trainees. The second day was dedicated to the EU legal framework regarding transplantation, to donor process and other clinical cases opened to discussion from audience.

Simultaneous translation was available.

During the courses it was clearly explained to all participants the possibility to read the full version of QMSGuide by Internet on the MoH web site (since the beginning of October 2007): www.health.gov.sk.

In the Assessment section, there will be added some technical comments to these courses.

Activities of Component IV:

Preparation of guidelines, booklet,info and CD,information leaflets and dissemination materials

All the Activities will be described in this section and commented in the Assessment  section.

### 4.1, 4.2    Preparation of guidelines, brochure, leaflets  and dissemination materials

4.3    Preparation of Closing Conference

The mission related to this component was held  from November 13th to November 15th 2007. Participants met at Ruzinov hospital and they were STEs Ms Di Ciaccio (CNT-Roma), Ms Bariani (CNT-Roma), Ms Gentile (CNT-Roma), plus RTA, RTA-A, PM Prof Koller and DPM Dr Kuba. Furthermore a meeting was held at MoH between STEs, RTA , RTA-A and SPO Mr Skorvaga together with Ms Vallova (MoH) in order to discuss the mission's results and to plan further activities. They worked on : 1) Production of 1500 copies of a  color Brochure as sinthetic version of QMSGuide, with an annexed CD containing the full QMSGuide plus relevant Slovak legislation. It will be edited in English and Slovak language and will be distributed by MoH and SCOT  to ICUs involved in procurement, dialysis centers, transplantation and coordination centres (through Directors and Responsable persons); 2) Production of 5000 copies of a color Leaflet for public, written as a draft in English language and later translated into Slovak language for public dissemination, in order to support an awairness campaign towards donation and transplantation in Slovakia by MoH. It will be distributed through MoH and SCOT.

3) Preparation of the 2008 Final Conference (especially regarding the related national Press Conference), to be held at MoH on November 5th 2008 (to be confirmed). The relevance of the conference should be at a national and international level.

Activity 4.1 consisted of preparation of a brochure as a tool of better coordination and management of organs, tissues and cells donations, and will be used by medical professionals and transplant coordinators. The brochure will have a general part explaining the Directive 2004/23/EC and related EU Directives. The CD annexed to the brochure will report the relevant Slovak legislation and the full QMSGuide and it will be focused on removal of the critical aspect identified in the audit activity and its general conclusions. The final part will regard the aspects related to the detection and handling of potential donors.

The brochure will be a synthetic version on paper of the guidelines (QMSGuide), and will be  produced in color version and 1500 copies. The languages for brochures and guidelines are Slovak and English.

The leaflet will be prepared by the STEs in a color version and 5000 copies will be printed within the project budget. It will be directed to public, written in English language and later translated into Slovak language for public dissemination, in order to support an awairness campaign towards donation and transplantation in Slovakia by MoH.

The reason why Activity 4.2 is foreseen is the fact that the project strives to improve the interaction and communication between the health care institutions and social community especially regarding the organ donation and transplantation.

The dissemination materials will be prepared taking into consideration that a possible subsequent public awareness campaign will be launched by competent Slovak authorities.

There will be a provision of effective information on how to assure the Slovak community of:

- the procedures used from the ethical and health authority point of view for organ    transplants

- the important life saving results of those interventions

- the results obtained in other European countries.

Information material will cover organization of centers, coordination, control and evaluation programs, features that ensure transparency and quality of the Service as well as the main activities carried out by the National Transplant Center in Slovakia. Particular attention will also be devoted to organ donation, taking into account Slovak legislation in this specific field.

The drafts of the Brochure and Leaflet, developed during Component IV but to be completed in some parts, are enclosed as Annex 3.

For the printing company, a marketing research must be done in compliance with the legislation on the Public procurement.

4th STEERING COMMITTEE MEETING

On November 22nd, 2007 the 4th Steering Committee Meeting was held at MoH. The participants were: RTA Mr Lauro, RTA -A Ms Kotzigova, SPO Mr Skorvaga, Ms Vallova (MoH), IT PL Mr Nanni Costa, PM Mr Koller, DPM Mr Kuba, CFCU representative Mr Skvarka.

The progress of the TWproject and the plan for 2008 was discussed as well as the 4th quarterly report.

## Timing & Delays

### Adherence to schedule

In the fourth quarter, there have been implemented the activities of Component 2 and 4 according to the schedule of the twinning work-plan.  A minor change in  Component 3 was foreseen (as previously reported in 3rd quarterly report) due to other missions planned after the software-tender: whenever the IT company will be ready to start to work on software development (by December 2007 as per TW contract), DPM Mr Kuba from Slovak side and STEs Mr Ghirardini and Ms Scaglia from Italian side will take action in order to drive the IT company in its work. Other missions of Italian STE in Bratislava -regarding software development-  will be agreed between STE themselves and DPM Mr Kuba in 2008: this topic was fully debated by RTA with SPO Mr Skorvaga at October monthly meeting.

About activity 4.1 and 4.2 of Component IV, the draft of Brochure and Leaflet was developed within the project frame: after printing, the dissemination activity will be held during 2008 as per contract.

| Project Month |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 3. Development of a specific software |
| 3.1 preparation of the unified information system |  |  |  |  |  |  |  |  |  |  |  |

Expected to be delayed

### Recuperation of delays

Regarding  Component 3, activity 3.1 (Preparation of Unified Information System) will foresee other missions after the tender (month 13) for the reasons explained above while activity 3.2 (public procurement for Slovak IT company plus beginning of activity of Slovak IT company) is foreseen in adherence with TW project  time frame, as well as activity 3.3 (pilot testing, due between August and November 2008).

Development of activity 4.3 (closing conference and connected dissemination of material) is foreseen in adherence with time schedule.

## ASSESSMENT

### Overall assessment of progress

The Audits performed last February 07 were the first necessary step in order to develop and write an appropriate QMSGuide, updated and adherent to the real transplant situation of Slovakia: therefore the application of EU Directives (main aim of the QMSGuide) is performed with adherence to the Slovak transplant reality in 2007.

Under this point of view, the participation of Slovak experts in organ, tissue and cell field was implemented in order to have even a better picture of the legal framework and the real need of the transplant centres. On the other hand, the QMSGuide was really necessary in order to update and substitute the quality system guides owned by single transplant centers, and to make EU Directives fully fostered by transplant centers. Furthermore, every Guide needs to be read and applied on the field: this was the reason to run Medium Term courses inside the twinning project, in order to foster the conformity with the EU Directives reported inside the QMSGuide for Slovakia.

Regarding Short Term Courses, they were foreseen inside the project in order to update the training of coordinators and anesthesiologists among Slovakia: Site Visits by STEs were useful in order to plan such a course - appropriated to Slovak coordination centres and SCOT's reality.

The need to implement a real network between coordination centres, SCOT and transplant centres - and to have a real updated tool in order to obtain this goal - was the main reason to develop a new specific software. Through few missions, STEs could get a clear picture of the real situation of the old software at SCOT in Bratislava and of the unified information system that is nowadays being used in Slovakia among transplant centres, in order to write the appropriate requirements of public tender for the Slovak IT company. The need to implement a new hardware was added as well, in order to support better the development of the software. As previously reported,  new missions of STEs will be necessary when the IT Company will be ready to start, in order to make a common plan of action.

Component IV   was implemented in order to “advertise” the project among centres in Slovakia but with the ultimate aim to give tools to them and MoH to increase public awareness towards donation in Slovakia, increasing consequently transplantation.

#### Activities and goals  achieved during the reported framework  : Component IV and Component II

Component IV was developed during November 2007, in order to achieve its real goal in 2008: to spread the project out among Slovak coordination and transplantation centres, as well as to increase public awareness towards donation implementing, consequently, transplantation. This last issue will be deepened in the „issue arisen“  section.

The main goal of Component  II  was only partially achieved , due to the lack of participation of few centres to the courses: anyhow the majority of centres (around 66%)  participated and learned how to handle and use on a daily working basis the QMSGuide and  consequently to foster the EU directives regarding tissue and cell transplantation and EU suggestions regarding organs.

This topic, and the need of MoH 2008 Audits (monitoring) in order to verify the application of QMSGuide  by centres in Slovakia,  will be fully debated inside the „issue arisen“ section as well.

#### Following activities :

COMPONENT III

Component III (development of a specific software) and its activities 3.2 and 3.3 will be developed starting by December 2007, in close collaboration between Italian STEs Mr Ghirardini and Ms Scaglia and DPM Mr Kuba, responsible for the software at SCOT- Bratislava. The starting activity of IT company will be carried out no later than end of the year (as foreseen in the project). The need for other missions of STEs has already been reported.

Finally the pilot testing (activity 3.3) for the new software will be performed between August and November 2008.

COMPONENT IV

Activity 4.3 (closing conference and connected dissemination of material) will be held by November 2008.

The Final Conference (with the related press conference) will be prepared in order to have an high relevance nationally and internationally and it will be held at MoH on November 5th, 2008 (to be confirmed).

One of the major goals of the conference, in addition to the presentation of the results of the project, will be to focus the attention of the general Slovak public on the issues related to the transplantation of organs and tissues; therefore it should have high relevance nationally and be perceived by the general public also as an important international event.

The methods involved in the organization of a scientific event, as well as the one used for a dissemination event, will be applied.

The persons invited to participate will be selected according to the criteria of institutional representation and public visibility.

Special attention will be given in involving the media both at the national, European and international level.

The conference will last one day and will be followed by a press conference, in which Slovak and Italian authorities, the PLs, RTA and other  persons involved in the project, will illustrate to the press the obtained results .

During the conference , the dissemination materials will be presented to the press and distributed.

It was agreed that the Dissemination of informative materials will start at the beginning of 2008 and will follow over the whole year.

### Issues arisen

- Participation at Short and Medium Term Courses

It is worthwhile to underline that the overall participation to these courses was represented by 57 trainees all together, instead of 100 as foreseen inside the TW contract; moreover, the duration of Medium Term Courses was reduced to 7 days instead of 8 because of poor number of participants to last MTC 4 course.

There are 4 main explanations or remarks to this topic, all of them fully debated and agreed at the October monthly meeting with SPO Mr Skorvaga:

1) 100 participants, as foreseen inside the original TW contract, were probably too many (average 2-3 participants per centre =  around 70 participants maximally, considering all together transplant and coordination centres in Slovakia);

- the financial support was part of the problem but, affording the travel and accomodation expenses of participants by SK MoH (or by Hospitals themselves - as it was stated by MoH), it would have increased the attendance  to the courses .

PM Mr Koller as well as the twinning team received many phone calls from transplant centres complaining about this issue;

3)  the project was very well advertised during 2007 (RTA trips through centres, Kick off Meeting in Bratislava, Audits by STEs, Audit Conference in Bratislava, Site Visits by STEs, Scientific Meetings where RTA was invited in all main towns among Slovakia) but maybe it was little advertised in the previous year 2006 - people working inside the centres needed probably more  time to „digest“ and get acquainted to such a huge national project  and to understand the importance to participate in it;

4)  in some centers there are just few people actively working, so they probably did not have the opportunity to attend the courses, due to their poor number and amount of daily work.

Last remark is, again, the lack of sense of „whole national transplant community“ between centres themselves and with national institutions (SCOT, MoH)-as it was stated previously by Italian PL Mr Nanni Costa: this lack could have been contributed to this lower participation as well.

Regarding this last topic, the work done by scientific societies like Slovak Transplant Society is foreseen by Twinning team as essential in contribution for the re-building of the whole transplant system in Slovakia.

- Increased number of donations in Slovakia in year 2007

The TW project  has probably contributed to increase the total number of Slovak donors collected so far (more than 100 donors  up to date since the beginning of year 2007): in fact, comparing to the same period of year 2006, the number of donors in Slovakia  has raised notably (almost doubled), probably as a “twinning” effect and because of the new slovak laws on transplantation discussed in the previous report.

Remarkably , in 2004 there were 10.2 donations per 1 million of inhabitants in organ transplantation in Slovakia, while in 2007 it was achieved almost 20 donations per 1 million of inhabitans.

#### Relationships between transplant centres and MoH: the idea of a “transplant community”and the need of financial support to SCOT, coordination and transplant centres

As already reported, during the Audit Report Conference, held last March 07 at MoH in Bratislava, Italian PL Mr Nanni Costa suggested that the best way to improve the relationship between transplant centres themselves and with MoH is to act all together as a whole transplant community, fully interconnected and tied up by clinical and scientific relationships.  Another option should be to empower SCOT, creating a different institution acting as a National Transplant Centre. This National Transplant Centre in Slovakia could support and manage the whole process of organ donation in cooperation with the regional coordinating units, having a better knowledge of local factors. It could either implement operational policies covering all aspects of the donation/transplant process and at the same time guarantee the fairness, transparency and safety of the whole system. Therefore this Central Institution  should guarantee the well-knowledge of the problems related to donation and transplantation, showing ability in problem solving and also controlling the entire process.

Slovak Transplant Society is working on this topic in collaboration with MoH.

But anyhow, in order to create a “new” SCOT as an institution fully independent and functioning, a financial support will be necessary.

The same need of financial support was claimed by all the transplant  and coordination centres, during RTA first trip along Slovakia and during the Audits and Site Visits as well: this issue must be fully considered by SK competent health care authorities.

#### Meetings with selected public bodies (scientific societies) convened by the RTA and his RTA Counterpart

This activity is foreseen by twinning team as an essential part in order to increase the awareness along Slovakia towards the development and goal of the TW project, and it can be foreseen as a part of the activity 4.2.

In strict collaboration with PM Mr Koller and DPM Mr Kuba, the twinning team planned meetings with some scientific societies where RTA was invited to present the project, as already reported inside the 2nd and 3rd quarterly report.

Apart from the  meetings described inside the previous quarterly reports, RTA was invited (through CNT-Roma) in Coccaglio (Brescia -Italy) on 13.10.07, where he presented and discussed the twinning project at the International Conference  on “ Organ,tissue,cell and blood donation worldwide: comparison between different international experiences”, reporting the progress of the  project in Slovakia.

The meeting represented a good opportunity to  better explain the steps of the project to an international audience , comparing this experience with different international ones.

Moreover, RTA and IT PL were invited  at the 2008 CH-SK Bilateral Transplant Conference, that  it will be run by Czech and Slovak Transplant Societies and held in Slovakia on September 2008 : there will be a specific session dedicated to the results of the Twinning project.

#### Liver Transplantation: the “extra twinning activity”

The following part of the text (liver transplantation: the extra-twinning activity) is mentioned only with an  informative aim because it is not foreseen inside the twinning contact and it is clearly an extra twinning activity.

On September 07, RTA Mr Lauro spoke with representative of EU Commission Mr Bregeon about the possible agreement between Italy and Slovakia on liver transplantation (as  reported inside the previous reports).

On October 31st, 2007 some REMARKS by MoH on the agreement (called by now “Declaration of Intent”) were received by IT PL Mr Nanni Costa: the agreement was written again following the remarks and presented to MoH one week later.

As a consequence, on November 20th , 2007 the IT PL Mr Nanni Costa met Mr Fernandez-Zincke , representative for Organ Transplantation of the EU Commission – Health and Consumer Protection- Directorate General in order to talk about this possible agreement between Italy and Slovakia on liver transplantation.

Furthermore, on November 22nd, 2007  Mr Nanni Costa came to Bratislava in order to discuss with  MoH representative Ms Liptakova  the new MoH remarks on the 2nd version of Declaration of Intent.

This possible common project on liver transplantation between Italy and Slovakia was useful to the twinning project for the following reason, even if it is clearly an extra twinning activity, outside the goal of the project.

Marginal donors were taken into account as potential liver donors to be offered abroad, if not used for Slovak cirrhotic patients.

Up to half of November 2007 Italy, through a CNT organization called “Italian Gate to Europe” in Rome, got 12 marginal livers from Slovakia for 12 cirrhotic recipients since “two days visit” of Slovak experts on March 2007 in Italy (previously reported): 3 livers went to Bologna, 5 to Modena,2 to Ancona, 1 to Torino and 1 to Roma.

All these 12  recipients were transplanted and in good conditions after liver transplantation.

Other two marginal livers were offered by Slovakia to Italy but not used  for problems related to the flight connection.

This fact has contributed to increase the total number of Slovak liver donors collected so far :  37 liver donors in Slovakia up to October 07 (only 20 livers in whole 2006,almost doubled) .

They were sent to Czech Republic 19 livers, to Italy 12 livers, to Austria 4 and to Germany 2.

Regarding the Coordination Centres, Martin harvested 17 livers (10 to Italy-in 2006 Martin harvested only 3 livers),  Bratislava 9 (6 to Czech Republic),  Banska Bystrica 6 (all to Czech Republic) and Kosice 5 (2 to Italy).

### Recommendations

Medium Term courses were attended by the majority of transplant centres but it will be necessary by MoH to verify through internal MoH 2008 Audits if QMSGuide (and the EU Directives reported inside) will be apply on the field in 2008 , especially by those centers not participating to the course.

These internal Audits should happen earlier than the Final Conference on November 2008, before advertising and disseminating the results of the project to the public. In fact one of the Benchmarks of the project is that the facilities included in the project will be accredited by the beginning of 2009, fulfilling the requirement of the directive 2004/23/EC.

The brochure (as a synthetic version of QMSGuide)  will help the knowledge of the EU Directives by centers as well as the internet publication on MoH web site of the QMSGuide will reinforce  it .

The leaflet will support the public campaign, held by MoH, towards donation and transplantation in Slovakia.

The Final Conference will raise the donation and transplantation issue in Slovakia to a national and international level.

The topic of Short Term courses  will necessitate to be repeated from time to time, as it has already been designed and organized by local slovak committee of ETCO  in 2005 and 2007.

The old software needed to be updated and it will be realized by the project, taking into account that also a hardware should be necessary in order to fully support the SW.

SCOT needs to be empowered as a new National Tranplant Center , as well as the network between coordination and transplant centres, realizing a real “transplant community”, interacting scientifically and medically between themselves and  with MoH.

Financial support needs to be foreseen in next years to fully support the „new SCOT“  and this transplant community: the work of Slovak Transplant Society in this direction is foreseen as essential step to create a new national transplant programme.

Liver transplantation needs to be implemented in Slovak Republic .

All possible agreements with other countries must be foreseen as just an initial step towards full independence of Slovakia on an own liver transplantation programme: the mortality rate of cirrhotic patients in Slovakia is still triple compared to other EU countries and this must be addressed and corrected by MoH through appropriate action. The presence of a own liver transplantation programme will increase organ donation in Slovakia as well.

EXPENDITURE TABLE

# ANNEX 1

- PROGRAMME OF STCourse

Short-term Course for Professionals working

in Organ  Procurement for transplantation

- VENUE:

Bratislava  15-16 October 2007

(Ruzinov hospital)

- PARTICIPANTS:

Local coordinators and anesthesiologists

- SIMULTANEOUS TRANSLATION WILL BE AVAILABLE

PROGRAM

DAY 1 (15th  OCTOBER)

| 9.00 – 9.15 | Welcome |
| --- | --- |
|  | Kuba |
| 9.15 – 9.30 | Slovakia: Italy Twinning Project |
|  | Lauro |
| 9.30 – 9.50 | Coordination organizative model- Bratislava |
|  | Vateha |
| 9.50 – 10.10 | Coordination organizative model- Martin |
|  | Miklusica |
| 10.10 – 10.30 | Coordination organizative model- Banska Bystrica |
|  | Sykora |
| 10.30 – 10.50 | Coordination organizative model – Kosice |
|  | Bena |
| 10.50 – 11.20 | COFFEE |
| 11.20 – 11.40 | Regional organizative coordination model in Itay |
|  | Ridolfi |
| 11.40 – 13.00 | Round table: proposal of coordination model in SK regions |
| 13.00- 14.00 | LUNCH |
| 14.00 – 14.20. | Model of national coordination in SK |
|  | Kuba |
| 14.20 – 14.40 | Model of national coordination in Italy |
|  | Nanni Costa |
| 14.40–15.40 | Round table: proposal of national coordination model of donations in SK |
| 15.40–16.00 | Discussion |
| 16.00 | Afternoon Tea |
| Evening | TWINNING DINNER |

DAY 2 (16th OCTOBER)

| 8.30 – 9.30 | Tools to increase organ procurement |
| --- | --- |
|  | Zanello |
| 9.30 – 10.30 | Comparison on safety of donor |
|  | Pettinao |
| 10.30 – 11.00 | COFFEE |
| 11.00 – 13.00 | Discussion on clinical cases related to course topics |
|  | Giordano(+ Zanello, Pettinao, Ridolfi+Vateha,Miklusica,Sykora,Bena) |
| 13.00 – 13.30 | Conclusions and final remarks |
| 13.30 | LUNCH and HOME |

- LIST OF potential PARTICIPANTS TO STCOURSE

- STCourse report

Report regarding the outcome of the Short term Course for coordinators and anesthesiologists organized in Bratislava between 15 and 16 October 2007

The analysis regarding comparison between the National transplant coordination systems

The discussion led to general conclusions, shared by the Slovak and Italian professionals.

It would be advisable that  SCOT consolidates its operational role inside the Slovak reality, cooperating in order to realize the efforts implemented during the donation process – realized at the moment only at a peripheral level – managing to create, in this way, a strategy based on the “national transplant network ”.

Here there are the presumed instruments that could be used:

1) SCOT should be involved into the coordination of the donation process, as a leader in the “problem solving” field ( transport , the centralization of the exams performed out of the donation site, the provision of national programs regarding the transplant for hyper immunized patients, etc.)

2) SCOT should provide the national guidelines concerning the criteria for inclusion in the waiting list and the allocation of organs donated, encouraging the exchanges between the different Transplant Centers in Slovakia.

3) The coordination of the import/export process that includes the organ, to or from other countries.

4) There should be a more penetrating role while informing the national media regarding the donation and transplant.

5) There should be taken a national informative campaign regarding the donation and the transplant.

6) Implement the on-line connection between the Donor Centers and the Transplant Centers, through a network aimed to optimize the donations.

7) The need of clear and nationwide known waiting lists.

8) Provide the entire network with the follow-up of the patients affected by organ transplant, as well as with the results of the tissue banks. The national recognition of the role played by the local coordinators in the donation process could encourage this strategy based on the “national transplant network”. This could also indicate to the responsables of the Slovak Health Authority an uniform national administrative position concerning this professional category, essential for the success of the system. There have been discussions regarding the necessary financial support aimed to optimize the system.

The comparison between different ways of regional transplant coordination

The discussion led to conclusions shared by the Slovak professionals (the transplant coordination from Bratislava, Martin and Kosice) and the Italian ones. The critical elements noticed inside the Slovak transplant system were the following:

-the local coordinator represents the critical step of the system, and he/she is the one that should be recognized and emphasized;

-even inside a system characterized by a high transplantologic culture, the continuous training has to be performed, especially when we speak about the eligibility criteria of the potential organ donors, according to patterns universally recognized;

-the communication between the four Slovak regional centers and the SCOT should be enhanced and realized in real-time;

-the centralization of the samplings and of all the  exams performed on the potential donor continues to be the only solution to the present condition, even if the role of peripheral hospitals is still important from a donative point of view;

-the importance of the informative campaign led by SCOT was unanimously recognized.

The discussion regarding:

- The strategies aimed to increase the number of donors,

- The donor’s safety,

- The clinical cases

The discussion is considered to have been profitable for the reciprocal exchange of operational procedures.

Lorenza Ridolfi

(report approved by Mr Kuba)

# ANNEX 2

- PROGRAMME OF MTCourses

COURSE MTC 1

Safety and Quality of Organs,Tissues and Cells for Human Application

A Training Course for Professionals working in Tissue or Cell Procurement, Processing, Storage or Distribution and Organ Transplantation

Venue:  The Library, Ruzinov Hospital, Bratislava

DAY 1 (18TH SEPTEMBER)

| 9.00 – 9.15 | Welcome |
| --- | --- |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 9.15 – 9.30 | Participant introductions |
| 9.30 – 10.00 | Slovakia:Italy Twinning Project |
|  | Dr Augusto Lauro |
| 10.00 – 10.30 | Slovak Legal Framework |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 10.30 – 11.00 | COFFEE |
| 11.00 – 11.30 | Quality System Guide Overview |
|  | Dr Deirdre Fehily |
| 11.30 – 11.50 | Quality System Guide – Organs |
|  | Dr Giuseppe Piccolo |
| 11.50 – 12.10 | Quality System Guide – Cells |
|  | Dr . Giovanni Migliaccio |
| 12.10 – 12.30 | Quality System Guide – Tissues |
|  | Dr Deirdre Fehily |
| 12.30 – 13.00 | Quality System Guide - General Discussion |
| 13.00- 14.00 | LUNCH |
| 14.00–15.30 | Practical Examples of Quality System Management – participation of all attendees |
|  | Facilitators: Stefan Poniatowski, Deirdre Fehily, Giuseppe Piccolo |
| 15.30–16.00 | Discussion of Free Quality System cases from Slovak centres |
|  | Facilitators: Stefan Poniatowski, Deirdre Fehily, Giuseppe Piccolo |
| 16.00 | Afternoon Tea |
| Evening | TWINNING DINNER |

DAY 2 (19TH SEPTEMBER)

| 8.00 – 8.30 | Donor Selection and Procurement |
| --- | --- |
|  | Dr Maurizio Valeri |
| 8.30 – 9.30 | Donor Selection Cases – participation of all attendees |
|  | Facilitators: Dr Valeri, Dr Porta |
| 9.30 – 10.30 | Implementing Quality System Requirements for Bone Marrow and Peripheral Blood Stem Cells – some challenges (including 20 minutes discussion) |
|  | Dr Martino Introna |
| 10.30 – 11.00 | COFFEE |
| 11.00 – 11.40 | Implementing Quality System Requirements for Tissues – some challenges (including 10 minutes discussion) |
|  | Stefan Poniatowski |
| 11.40 – 12.20 | Achieving quality, safety and sufficiency in organ donation and transplantation (including 10 minutes discussion) |
|  | Dr Piccolo |
| 12.20 – 13.00 | EU Legal Framework |
|  | Thomas Bregeon, European Commission |
| 13.00 – 13.30 | Conclusions and final remarks |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 13.30 | LUNCH and HOME |

COURSE MTC 2

Safety and Quality of Organs, Tissues and Cells for Human Application

A Training Course for Professionals working in Tissue or Cell Procurement, Processing, Storage or Distribution and Organ Transplantation

Venue:  The Library, Ruzinov Hospital, Bratislava

DAY 1 (20TH SEPTEMBER)

| 9.00 – 9.15 | Welcome |
| --- | --- |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 9.15 – 9.30 | Participant introductions |
| 9.30 – 10.00 | Slovakia:Italy Twinning Project |
|  | Dr Augusto Lauro |
| 10.00 – 10.30 | EU Legal Framework |
|  | Thomas Bregeon, European Commission |
| 10.30 – 11.00 | Slovak Legal Framework |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 11.00 – 11.30 | COFFEE |
| 11.30 – 12.00 | Quality System Guide Overview |
|  | Dr Deirdre Fehily |
| 12.00 – 12.15 | Quality System Guide – Organs |
|  | Dr Giuseppe Piccolo |
| 12.15 -12.30 | Quality System Guide – Cells |
|  | Dr . Giovanni Migliaccio |
| 12.30 – 12.45 | Quality System Guide – Tissues |
|  | Dr Deirdre Fehily |
| 12.45 – 13.00 | Quality System Guide - General Discussion |
| 13.00- 14.00 | LUNCH |
| 14.00–15.30 | Practical Examples of Quality System Management – participation of all attendees |
|  | Facilitators: Stefan Poniatowski, Deirdre Fehily, Giuseppe Piccolo |
| 15.30–16.00 | Discussion of Free Quality System cases from Slovak centres |
|  | Facilitators: Stefan Poniatowski, Deirdre Fehily, Giuseppe Piccolo |
| 16.00 | Afternoon Tea |
| Evening | TWINNING DINNER |

DAY 2 (21ST SEPTEMBER)

| 8.00 – 8.30 | Donor Selection and Procurement |
| --- | --- |
|  | Dr Maurizio Valeri |
| 8.30 – 9.30 | Donor Selection Cases – participation of all attendees |
|  | Facilitators: Dr Valeri, Dr Porta |
| 9.30 – 10.30 | Implementing Quality System Requirements for Bone Marrow and Peripheral Blood Stem Cells – some challenges (including 20 minutes discussion) |
|  | Dr Martino Introna |
| 10.30 – 11.00 | COFFEE |
| 11.00 – 12.00 | Implementing Quality System Requirements for Tissues – some challenges (including 20 minutes discussion) |
|  | Stefan Poniatowski |
| 12.00 – 13.00 | Achieving quality, safety and sufficiency in organ donation and transplantation (including 20 minutes discussion) |
|  | Dr Piccolo |
| 13.00 – 13.30 | Conclusions and final remarks |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 13.30 | LUNCH and HOME |

COURSE MTC 3

Safety and Quality of Organs, Tissues and Cells for Human Application

A Training Course for Professionals working in Tissue or Cell Procurement, Processing, Storage or Distribution and Organ Transplantation

Venue:  The Library, Ruzinov Hospital, Bratislava

DAY 1 (25TH SEPTEMBER)

| 9.00 – 9.15 | Welcome |
| --- | --- |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 9.15 – 9.30 | Participant introductions |
| 9.30 – 10.00 | Slovakia:Italy Twinning Project |
|  | Dr Augusto Lauro |
| 10.00 - 10.30 | Slovak Legal Framework |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 10.30 - 11.00 | COFFEE |
| 11.00 - 11.30 | Quality System Guide Overview |
|  | Dr . Fiorenza Bariani |
| 11.30 – 11.50 | Quality System Guide – Organs |
|  | Dr Giuseppe Piccolo |
| 11.50 – 12.20 | Quality System Guide – Tissues and Cells |
|  | Dr Deirdre Fehily |
| 12.20 – 13.00 | Quality System Guide - General Discussion |
| 13.00- 14.00 | LUNCH |
| 14.00–15.30 | Practical Examples of Quality System Management – participation of all attendees |
|  | Facilitators: Valéria Jarabinska, Deirdre Fehily, Giuseppe Piccolo |
| 15.30–16.00 | Discussion of Free Quality System cases from Slovak centres |
|  | Facilitators: Valéria Jarabinska, Deirdre Fehily, Giuseppe Piccolo |
| 16.00 | Afternoon Tea |
| Evening | TWINNING DINNER |

DAY 2 (26TH SEPTEMBER)

| 8.00 – 8.30 | Donor Selection and Procurement |
| --- | --- |
|  | Dr Maurizio Valeri |
| 8.30 – 9.30 | Donor Selection Cases – participation of all attendees |
|  | Facilitators: Dr Valeri, Dr Elisa Pianigiani |
| 9.30 – 10.30 | Implementing Quality System Requirements for Bone Marrow and Peripheral Blood Stem Cells – some challenges (including 20 minutes discussion) |
|  | Dr Letizia Lombardini |
| 10.30 – 11.00 | COFFEE |
| 11.00 – 11.40 | Implementing Quality System Requirements for Tissues – some challenges (including 10 minutes discussion) |
|  | Dr Elisa Pianigiani |
| 11.40 – 12.20 | Achieving quality, safety and sufficiency in organ donation and transplantation (including 10 minutes discussion) |
|  | Dr Piccolo |
| 12.20 – 13.00 | EU Legal Framework |
|  | Eduardo Fernandez Zincke/Caroline Trouet, European Commission |
| 13.00 – 13.30 | Conclusions and final remarks |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 13.30 | LUNCH and HOME |

COURSE MTC 4

Safety and Quality of Organs, Tissues and Cells for Human Application

A Training Course for Professionals working in Tissue or Cell Procurement, Processing, Storage or Distribution and Organ Transplantation

Venue:  The Library, Ruzinov Hospital, Bratislava

DAY 1 (27TH SEPTEMBER)

| 9.00 – 9.15 | Welcome |
| --- | --- |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 9.15 – 9.30 | Participant introductions |
| 9.30 – 10.00 | Slovakia:Italy Twinning Project |
|  | Dr Augusto Lauro |
| 10.00 – 10.30 | EU Legal Framework |
|  | Eduardo Fernandez Zincke/Caroline Trouet, European Commission |
| 10.30 – 11.00 | Slovak Legal Framework |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 10.30 - 11.00 | COFFEE |
| 11.00 - 11.30 | Quality System Guide Overview |
|  | Dr . Fiorenza Bariani |
| 11.30 – 12.00 | Quality System Guide – Organs |
|  | Dr Giuseppe Piccolo |
| 12.00 – 12.20 | Quality System Guide – Tissues and Cells |
|  | Dr Deirdre Fehily |
| 12.20 – 13.00 | Quality System Guide - General Discussion |
| 13.00 - 14.00 | LUNCH |
| 14.00–15.30 | Practical Examples of Quality System Management – participation of all attendees |
|  | Facilitators: Valéria Jarabinska, Deirdre Fehily, Giuseppe Piccolo |
| 15.30–16.00 | Discussion of Free Quality System cases from Slovak centres |
|  | Facilitators: Valéria Jarabinska, Deirdre Fehily, Giuseppe Piccolo |
| 16.00 | Afternoon Tea |
| Evening | TWINNING DINNER |

DAY 2 (28TH SEPTEMBER)

| 8.00 – 8.30 | Donor Selection and Procurement |
| --- | --- |
|  | Dr Maurizio Valeri |
| 8.30 – 9.30 | Donor Selection Cases – participation of all attendees |
|  | Facilitators: Dr Valeri, Dr Elisa Pianigiani |
| 9.30 – 10.30 | Implementing Quality System Requirements for Bone Marrow and Peripheral Blood Stem Cells – some challenges (including 20 minutes discussion) |
|  | Dr Letizia Lombardini |
| 10.30 – 11.00 | COFFEE |
| 11.00 – 12.00 | Implementing Quality System Requirements for Tissues – some challenges (including 10 minutes discussion) |
|  | Dr Elisa Pianigiani |
| 12.00 – 13.00 | Achieving quality, safety and sufficiency in organ donation and transplantation (including 10 minutes discussion) |
|  | Dr Piccolo |
| 13.00 – 13.30 | Conclusions and final remarks |
|  | Dr Jan Koller/Dr Daniel Kuba |
| 13.30 | LUNCH and HOME |

# ANNEX 3

Draft of LEAFLET

for general public

Importance of organ, tissue and cell donation

Transplantation of organs, cells and tissues are acknowledged as effective therapies across a wide range of both fatal and non-fatal disease.

Nowadays, thanks to transplantation, we can offer a better life to those who are suffering.

Transplant means a new life: recipients would get back to normal life, they would work again, have children, play sports, they would LIVE!

This is the meaning of donation. Donate organs, tissues and cells means donate life. Choosing to be a donor is choosing to be active part of a solidaristic community. Helping an ill person is helping the society to grow up! Everyone of us has an unlimited possibility to offer gifts for life.

Donation in Slovak Republic

to be completed by Dr. Kuba

Transplant programs presently running in Slovak Republic, organization of transplant centres, coordinating centres

As regards organ transplantation centers, all of them are under the responsibility of the MoH as follows:

- Slovak Centre for Organ Transplantation – Slovak Medical University (SCOT) with 5 Regional Transplantation centers

  - Transplant centre University Derer’s hospital, Bratislava (kidneys, liver)

  - Transplant centre, Slovak institute for heart diseases, Bratislava, (heart)

  - Transplant centre University hospital, Martin (kidneys)

  - Transplant centre Roosevelt hospital, Banska Bystrica (kidneys, pancreas)

  - Transplant centre, University hospital, Košice, (kidneys)

  - Children Cardio center, Bratislava (heart)

The first tissue establishment in the Slovak Republic was linked to Ružinov General Hospital in Bratislava and started its activity in 1988. The list of currently existing tissue establishments under the competence of the SR Ministry of Health is as follows:

- Central Tissue Bank, University Hospital Ružinov, Bratislava, multi-tissue bank

- Associated Tissue Bank, University Hospital and Medical School, Košice, multi-tissue bank

- International Eye Bank, Petržalka University Hospital, Bratislava , eye bank

- International Eye Bank, F.D.Roosewelt Hospital, Banská Bystrica, eye bank

- Hemopoietic Cell Banks  (HPC banks)  -  4 in Bratislava, 1 in Banska Bystrica, 1 in Martin, 1 in Kosice, 1 in Presov

- Children Faculty Hospital, Bratislava (blood cells, bone marrow)

- Faculty Hospital, Bratislava – Petržalka (blood cells)

In addition, there are non-governmental and private organisations such as:

- Slovak Register of Cord Haemopoetic Cells (EUROCORD), Bratislava, cord blood bank

- Privat Hospital Kosice - Saca Tissue Bank

The twinning program and its aims

A twinning project between the Italian and Slovak Ministries of Health, funded by the European Commission, began in December 2006 with the aim of improving the safety, quality and availability of organs, tissues and cells in the Slovak Republic. The project, running for two years, aims at introducing quality management principles for organ, tissue and cell transplantation, to assure highest possible levels of public health protection, that means the protection of the patient.

Some figures on donation and transplantation in Europe (Transplant Newsletter-Council of Europe)

Range of pmps in different EU countries, waiting lists and consequent importance of donation

5 Frequently Asked Questions, to be completed by Dr.Kuba

References

www.health.gov.sk

www.ncot.sk

Draft of BROCHURE

Index

The European policy in the field of organs, tissues and cells donation and transplantation.

The Slovak legislation

The twinning program between Italy and Slovak Republic

Critical aspects in the donor management and transplant process

The QMS guidelines

Annex: CD with guidelines

## The European policy

## in the field of organs, tissues and cells donation and transplantation

Benefits of transplantation

Organ transplantation is the most cost-effective treatment for end-stage renal failure, and it is the only available treatment for end-stage failure of organs such as the liver, lung, and heart. Transplantation of tissues such as corneas, cardiovascular tissues, bone, tendons and skin are all well-established therapeutic techniques. Although most of these transplants are not lifesaving, they can offer major therapeutic benefits to a wide range of patients. Cell transplantation, particularly haematopoietic progenitor cell (HPC) transplantation, is also well established and can be lifesaving in the treatment of severe immunodeficiency syndromes and many types of haematological malignancy.

European efforts

The complex process of donation and transplantation requires the adoption of high quality and safety standards as well as a good cooperation and harmonization of such standards among the Member States. In this light, different European authorities, such as the Health Committee of the Council of Europe and the European Commission concentrated their efforts to improve quality and safety of transplant process. As concerns legislation, in the field of tissue and cells, the European Union adopted the Directive 2004/23/EC on setting standards of quality and safety for the donation, procurement, testing, processing, preservation, storage and distribution of human tissues and cells and the two related Technical Directives (nn.17 and 86 published in 2006).

The first Directive (23/2004) states the general requirements, detailed in the two following technical directives. The 17/2006 establishes the donor selection criteria and the mandatory tests, including the provision for acceptance of non complying donations by risk assessment and a full list of exclusion criteria based on medical and social history and validity of blood sample. The mandatory tests includes

  - Anti-HIV 1 and 2

  - HbsAg

  - HBV anti-core

  - Anti-HCV

  - Syphilis (reactive test result – donor may still be eligible by risk assessment)

The second technical directive 86/2006 focuses on the requirements for the accreditation of establishments and processes, particularly on:

  - Quality system

  - Staff training requirements

  - Validation (through literature and retrospective analysis of own data)

  - Risk assessment

  - Reporting and communication of serious adverse events and reactions

All the European recommendations and legislation can be found on the following websites:

Council of europe SDPTO

European Commission Pub Health

## Slovak legislation

The following Slovak laws and Ministry of Health guidance constitute the legal framework for organ, tissue and cell transplantation in Slovakia:

- Law number 576/2004

This is the main transplant law which governs procurement, storage and transport of organs, tissues and cells.

- Law number 282 of April 19th 2006 represents an updating of Law number 576 to incorporate the requirements of other new legislation, including Directive 2004/23/EC (see 2.0 below).

- Governmental Decree 20/2007, published on December 20th 2006, is the transposition into Slovak law of Directive 2006/17/EC (see 2.0 below).

- The Slovak Ministry of Health Guidance published on the 3rd December 2006 (28610/2006 – OZSO) expanded on Law number 576, including greater details on organ donor selection requirements.

All legislation is attached as appendixes to QMS guidelines.

## The twinning program between Italy and Slovak Republic

Funded by the European Commission (DG Enlargement) through the Phare program, the twinning project entitled ‘Improvement of the Safety, Quality and Availability of Organs, Tissues and Cells between the Italian and Slovak Ministries of Health began in December 2006 and will continue for 2 years. The main components of the project are

- audits of existing activities;

- design and implementation of a Quality Management System Guide

- training courses;

- technical assistance in the development of a unified Information Technology system

- information and dissemination

The audits of organ, tissue and cell procurement and transplant centre allowed to draw a picture of present features of the Slovak system, focusing on its strengths and weaknesses. The audit reports set the grounds for the design of the QMS guidelines.

## Critical aspects in the donor management and transplant process

The results of audit visits were published on the Health Ministry website (www.health.gov.sk) and presented during a conference held in March 2007 in Bratislava.

Among the identified critical aspects in the donor management and transplant process, the following general needs were evinced:

- national competent authorities should be identified in order to coordinate, standardize and monitor the national donation and transplantation system;

- a national transplant community that shares knowledge, know-how, best practices and information concerning procurement, banking and transplant activities;

- a consistent quality system that identify and cover all steps of  the process from donor identification to transplant;

- a clear-cut definition of roles and tasks for involved personnel, taking into account the importance of training needs and educational programmes;

- clear job descriptions for each function and a clear organizational chart, with a description of the responsibilities for each activity and process;

- periodical audits by internal and external experts in order to ensure a continuous monitoring and improvement of the system;

- the adoption of better procedures always ensuring adequate safety levels for protection of healthcare professionals;

- necessity of adequate tools and facilities where processes take place, in the respect of existing rules.

## The QMS guidelines

The Quality Management System Guide (QMSG) aims to provide tools which will help to raise the quality of the whole transplantation process of organs, tissues and cells in Slovakia.  This guide has been developed by technical experts from the fields of organs, tissues and cells in Italy and Slovakia. The platform for the definition of quality and safety standards was provided by the three European Union Directives 2004/23/EC, 2006/17/EC, 2006/86/EC. A number of Italian, Slovakian and international documents have been consulted in the course of its development, notably the Council of Europe Guide to Safety and Quality Assurance for Organs, Tissues and Cells (3rd Edition). The guidance provided is consistent with current transplant legislation in Slovakia. The scope of this guide extends to quality assurance standards for procurement, preservation, processing and distribution for organs, tissues and cells of human origin (allogeneic and autologous) used for transplantation purposes. Blood, blood products and somatic and genetic cell therapy products and tissue engineered products are excluded from the scope of these guidelines. Genetically modified human materials are considered to be medicinal products (EU Directive 2004/27/EC) and additional requirements apply which are not included in this Guide.